## Sheet1
Team Member In-Charge | Deliverables | September |  |  | October |  |  | November |  |  |  |  | December |  |  |  |  | Jan
|  | 2020-09-17 | 2020-09-24 | 2020-09-27 | 2017-10-08 | 2020-10-15 | 2020-10-26 | 2020-11-03 | 2020-11-10 | 2020-11-12 | 2020-11-19 | 2020-11-26 | 2020-12-03 | 2020-12-10 | 2020-12-17 | 2020-12-24 | 2020-12-31 | 2021-01-07 | 2021-01-14 | 2021-01-21 | 2021-01-28
ALL | Project Briefing
ALL | Preliminary Exploration | [20 empty] | Initial | Name | Module Role
ALL | Gathering and Analysis of Related Works | [20 empty] | AG | Areeve Gam | Toolsmith, Developer
ALL | Customer Day: Requirement Gathering | [20 empty] | HT | Hui Ting | Scrum Master, Developer
ALL | Gantt chart (Milestones) | [20 empty] | ZA | Zainul Ariffin | Product Owner, Chief Architect, Developer
ALL | Architecture Roadmap of different phases | [20 empty] | JG | Jonathan Goh | QA Manager, Developer
ALL | Familiarisation with tools/SDK | [20 empty] | QG | Qi Guang | QA Manager, Developer
ALL | Class diagram and refined use case diagram | [20 empty] | ST | Sharon Ting | Toolsmith, Developer
ALL | System Architecture Roadmap of different phases
ALL | User research deliverables: e.g. class diagram and ER diagram, etc.
ALL | Customer Day: Design Demonstration
ALL | Adoption of agile SDLC methodology
ALL | Refined version of various diagrams
ALL | Backend development for key APIs | [20 empty] | Legend | Status
ALL | Building of the functional and feature elements | [21 empty] | Completed
ALL | Creation of database system | [21 empty] | Progress
ALL | Customer Day: System Demonstration | [20 empty] | * | Subject to Changes